## Summary
HR Platform — Task Summary by Role
Role | P0 Tasks | P1 Tasks | Feature Tasks | Total Tasks
Product Manager | 5 | 0 | 8 | 13
Platform Architect | 0 | 0 | 9 | 9
Developer | 8 | 11 | 6 | 25
Bug Hunter | 5 | 6 | 1 | 12
UI-UX Designer | 0 | 0 | 10 | 10
QA Engineer | 5 | 3 | 2 | 10
Security Analyst | 0 | 0 | 7 | 7
DevOps Hub | 0 | 0 | 9 | 9
Teaching Assistant | 0 | 0 | 6 | 6
TOTAL | 23 | 20 | 58 | 101

## Product Manager
Product Manager
Category | Priority | Task | Description | Module | Status
Requirements & Prioritization
Bug Triage | P0 | Triage full language support failure | 15/20 sections don't translate — define acceptance criteria & priority order | Platform-wide | To Do
Bug Triage | P0 | Triage legal entities dropdown bug | Empty dropdown blocks salary setup — define fix requirements | Employees | To Do
Bug Triage | P0 | Triage pipeline filter limitations | Only stage filter works — specify required filter set | Recruitment | To Do
Bug Triage | P0 | Triage bulk actions gap | No multi-select for candidates — write user story | Recruitment | To Do
Bug Triage | P0 | Triage shift notes gap | No way to attach notes to shifts — define spec | Attendance | To Do
Feature Specs |  | Write PRD: 1:1 Meetings module | Define meeting history, notes, shared agenda requirements | HR | To Do
Feature Specs |  | Write PRD: Performance Reviews | Scope 360° feedback, self-assessments, OKR goal setting | HR | To Do
Feature Specs |  | Write PRD: Employee Timeline | Define promotion/achievement/role-change tracking | HR | To Do
Feature Specs |  | Write PRD: Engagement Surveys | Define pulse checks & anonymous feedback flow | HR | To Do
Feature Specs |  | Write PRD: Mentorship Program | Scope auto-assign, scheduling, progress tracking, reports | HR | To Do
Feature Specs |  | Write PRD: Shift Self-Service | Cover My Schedule, availability, swap, reminders, confirmation | Attendance | To Do
Feature Specs |  | Write PRD: Integrations | Scope Calendar Sync, Teams, Zoom/Meet integrations | Platform | To Do
Roadmap |  | Prioritize 48 pending features into sprints | Balance P0 fixes, language support, and new features | All | To Do

## Platform Architect
Platform Architect
Category | Priority | Task | Description | Module | Status
System Design & Schemas
i18n Architecture |  | Design i18n framework overhaul | Current system fails on 15/20 sections — design robust translation pipeline | Platform-wide | To Do
i18n Architecture |  | Define translation key schema | Standardize key naming, fallback chains, plural rules | Platform-wide | To Do
Data Schema |  | Design legal entities data model | Fix empty dropdown — ensure entity-branch-wage relationships | Employees | To Do
Data Schema |  | Design recruitment filter indexes | Optimize for stage/source/date/recruiter queries | Recruitment | To Do
Data Schema |  | Design shift management schema | Support notes, swaps, availability, confirmations | Attendance | To Do
Integration |  | Design calendar sync architecture | Google Calendar + Outlook bidirectional sync | Platform | To Do
Integration |  | Design Teams and video conferencing layer | MS Teams + Zoom/Meet integration patterns | Platform | To Do
Performance |  | Design global search infrastructure | Cross-module search for employees, docs, settings | Platform-wide | To Do
Performance |  | Design session management system | Fix unchangeable timeout + filter persistence across nav | Platform-wide | To Do

## Developer
Developer
Category | Priority | Task | Description | Module | Status
Implementation & Coding
P0 — Language | P0 | Fix i18n for 15 broken sections | Salary, Departments, Org Structure, Recruiting, etc. | Platform-wide | To Do
P0 — Language | P0 | Fix My Portal profile translation | Profile page stays English on language switch | My Portal | To Do
P0 — Language | P0 | Fix Employees page translation | 'Add new employee' page stays English | Employees | To Do
P0 — Language | P0 | Fix Attendance button translations | 'Check out' and 'Remind' buttons stay English | Attendance | To Do
P0 — Data | P0 | Fix legal entities dropdown | Populate entity list in Primary Wage setup | Employees | To Do
P0 — Recruitment | P0 | Implement pipeline filters | Add source, date, recruiter filters | Recruitment | To Do
P0 — Recruitment | P0 | Implement bulk candidate actions | Multi-select move/reject in pipeline | Recruitment | To Do
P0 — Attendance | P0 | Implement shift notes | Add note/instruction field to shifts | Attendance | To Do
P1 Fixes | P1 | Fix session timeout settings | Make timeout configurable | Settings | To Do
P1 Fixes | P1 | Fix filter persistence on navigation | Preserve filters across page changes | Platform-wide | To Do
P1 Fixes | P1 | Fix Telegram language reset | Persist language choice across bot restarts | Telegram | To Do
P1 Fixes | P1 | Fix resume viewer (inline) | Open resumes inside candidate card, not new tab | Recruitment | To Do
P1 Fixes | P1 | Implement drag and drop file upload | Replace browse-only upload across platform | Platform-wide | To Do
P1 Fixes | P1 | Fix back button behavior | Navigate back without full page refresh | Navigation | To Do
P1 Fixes | P1 | Fix table and board view mismatch | 'Table view' click should open table, not board | Recruitment | To Do
P1 Fixes | P1 | Implement no-show tracking | Flag absent employees on shifts | Attendance | To Do
P1 Fixes | P1 | Enhance stage duration detail | Add granular time-in-stage metrics | Recruitment | To Do
P1 Fixes | P1 | Implement global search | Header search across employees, docs, settings | Platform-wide | To Do
P1 Fixes | P1 | Implement resume auto-parse | Extract phone, email from uploaded resumes | Recruitment | To Do
Features |  | Build 1:1 Meetings module | Meeting history, notes, shared agenda, private notes | HR | To Do
Features |  | Build Calendar Integration | Schedule meetings, events, reminders | HR | To Do
Features |  | Build Employee Timeline | Promotions, achievements, role changes log | HR | To Do
Features |  | Build Performance Reviews | 360° feedback + self-assessments | HR | To Do
Features |  | Build Goal Setting (OKRs) | Individual/team goal tracking | HR | To Do
Features |  | Build Shift Self-Service suite | My Schedule, availability, swaps, reminders, confirmation | Attendance | To Do

## Bug Hunter
Bug Hunter
Category | Priority | Task | Description | Module | Status
Finding & Fixing Bugs
P0 Bugs | P0 | Reproduce and document language failures | Test all 20 sections for translation issues, log exact failures | Platform-wide | To Do
P0 Bugs | P0 | Reproduce legal entities dropdown | Test across branches/roles, capture API response | Employees | To Do
P0 Bugs | P0 | Reproduce pipeline filter failures | Test each filter type, log which ones fail | Recruitment | To Do
P0 Bugs | P0 | Verify bulk actions are missing | Confirm no multi-select UI exists, check API support | Recruitment | To Do
P0 Bugs | P0 | Verify shift notes gap | Confirm no notes field in shift creation/edit | Attendance | To Do
P1 Bugs | P1 | Reproduce session timeout issue | Test settings page, verify timeout field behavior | Settings | To Do
P1 Bugs | P1 | Reproduce filter reset on navigation | Navigate between pages, verify filter state loss | Platform-wide | To Do
P1 Bugs | P1 | Reproduce Telegram language reset | Change language, restart bot, verify reversion | Telegram | To Do
P1 Bugs | P1 | Reproduce resume new-tab issue | Click resume, verify it opens new tab vs inline | Recruitment | To Do
P1 Bugs | P1 | Reproduce nav view mismatch | Click 'table view', verify it opens board view | Recruitment | To Do
P1 Bugs | P1 | Reproduce back button refresh | Use back button, verify full page reload | Navigation | To Do
Regression |  | Build regression test suite for i18n | Automated checks for all 20 sections after fix | Platform-wide | To Do

## UI-UX Designer
UI-UX Designer
Category | Priority | Task | Description | Module | Status
Interface & Experience
Bug-Related UX |  | Redesign language switcher UX | Ensure seamless full-platform language toggle | Platform-wide | To Do
Bug-Related UX |  | Design inline resume viewer | In-card scrollable resume viewer instead of new tab | Recruitment | To Do
Bug-Related UX |  | Design drag and drop upload zones | Consistent drop zones across all upload areas | Platform-wide | To Do
Bug-Related UX |  | Design global search bar | Header search with cross-module results | Platform-wide | To Do
New Features |  | Design 1:1 Meeting interface | Meeting scheduling, notes, shared agenda UI | HR | To Do
New Features |  | Design Performance Review flows | 360° feedback forms, self-assessment UI | HR | To Do
New Features |  | Design Employee Timeline view | Visual timeline of career events | HR | To Do
New Features |  | Design Shift Self-Service screens | My Schedule, availability picker, swap request flow | Attendance | To Do
New Features |  | Design Engagement Survey builder | Pulse check creation and anonymous response UI | HR | To Do
New Features |  | Design Mentorship Dashboard | Mentor-mentee pairing, progress tracking UI | HR | To Do

## QA Engineer
QA Engineer
Category | Priority | Task | Description | Module | Status
Testing & Quality
P0 Validation | P0 | Test i18n fix across all 20 sections | Verify each section translates fully in all languages | Platform-wide | To Do
P0 Validation | P0 | Test legal entities dropdown fix | Verify entities appear for all branches and roles | Employees | To Do
P0 Validation | P0 | Test pipeline filters | Verify stage, source, date, recruiter filters work | Recruitment | To Do
P0 Validation | P0 | Test bulk actions | Verify multi-select move/reject works correctly | Recruitment | To Do
P0 Validation | P0 | Test shift notes | Verify notes attach to and display on shifts | Attendance | To Do
P1 Validation | P1 | Test session timeout configurability | Change timeout, verify it persists | Settings | To Do
P1 Validation | P1 | Test filter persistence | Apply filters, navigate, verify they remain | Platform-wide | To Do
P1 Validation | P1 | Test Telegram language persistence | Change language, restart, verify it stays | Telegram | To Do
Regression Suite |  | Write regression tests for all P0 fixes | Automated test cases for each resolved P0 bug | All | To Do
Regression Suite |  | Write E2E tests for new features | Automated flows for 1:1, Timeline, Shift Self-Service | All | To Do

## Security Analyst
Security Analyst
Category | Priority | Task | Description | Module | Status
Security & Compliance
Audit |  | Audit session management security | Timeout is unchangeable — review session token handling | Settings | To Do
Audit |  | Audit i18n for injection risks | Test translation inputs for XSS/injection vectors | Platform-wide | To Do
Audit |  | Audit recruitment data access controls | Verify candidate PII is properly gated by role | Recruitment | To Do
Audit |  | Audit employee wage and entity data access | Verify salary data visible only to authorized roles | Employees | To Do
Compliance |  | Review GDPR compliance for surveys | Anonymous feedback must truly be anonymized | HR | To Do
Compliance |  | Review data retention for Telegram bot | Ensure language pref storage meets privacy policy | Telegram | To Do
Compliance |  | Validate integration auth flows | Audit OAuth for Calendar, Teams, video integrations | Platform | To Do

## DevOps Hub
DevOps Hub
Category | Priority | Task | Description | Module | Status
Deployment & Releases
Infrastructure |  | Set up i18n CI pipeline | Automated translation validation on every deploy | Platform-wide | To Do
Infrastructure |  | Configure feature flags for rollouts | Gradual rollout for 1:1, Timeline, Shift features | All | To Do
Infrastructure |  | Set up search infrastructure | Elasticsearch or Algolia for global search feature | Platform-wide | To Do
Monitoring |  | Add i18n monitoring dashboards | Track missing translations, fallback usage in prod | Platform-wide | To Do
Monitoring |  | Add recruitment pipeline metrics | Monitor filter usage, bulk action performance | Recruitment | To Do
Releases |  | Plan hotfix release for P0 bugs | Coordinate deploy for 5 critical fixes | All | To Do
Releases |  | Plan release for P1 bug batch | Bundle 11 P1 fixes into staged release | All | To Do
Integration Infra |  | Set up calendar sync workers | Background jobs for Google Calendar and Outlook sync | Platform | To Do
Integration Infra |  | Set up Teams and video webhooks | Webhook endpoints for MS Teams and Zoom/Meet | Platform | To Do

## Teaching Assistant
Teaching Assistant
Category | Priority | Task | Description | Module | Status
Learning & Understanding
Documentation |  | Document i18n translation process | Guide for adding/updating translations across sections | Platform-wide | To Do
Documentation |  | Document recruitment pipeline workflow | User guide for filters, bulk actions, stage management | Recruitment | To Do
Documentation |  | Document shift management features | User guide for notes, scheduling, self-service features | Attendance | To Do
Onboarding |  | Create onboarding guide for 1:1 Meetings | How-to for managers: schedule, note, agenda features | HR | To Do
Onboarding |  | Create onboarding guide for Performance Reviews | How-to for 360° feedback, OKRs, self-assessments | HR | To Do
Knowledge Base |  | Build initial Knowledge Base content | Core training materials for platform features | HR | To Do